## Sheet1
Activity | Time Line |  |  |  |  | Penanggung Jawab
| 13/10/2021 - 19/10/2021 | 20/10/2021-28/10/2021 | 29/10/2021-10/11/2021 | 11/11/2021-15/11/2021 | 16/11/2021-till semester exam
Data Preparation | Done |  |  |  |  | Ahmad Hanif Nurfauzi
Data Preprocessing |  | Done |  |  |  | Ahmad Hanif Nurfauzi
Define the model |  |  | Not Yet |  |  | Ahmad Hanif Nurfauzi
deployment |  |  |  | Not Yet |  | Ahmad Hanif Nurfauzi
bug fixing |  |  |  |  | Not Yet | Ahmad Hanif Nurfauzi